## Executive Summary
Magasinet KBH Acceptance Audit
Editable workbook export generated from the same evidence tables as the PDF report.
Verdict | Reject/refund candidate
Required capabilities scored | 61
Required full | 27
Required partial | 25
Required skipped | 9
High-impact required gaps (impact >= 8) | 13
Critical audit findings (9-10) | 18
Severe mocked/hardcoded findings (>= 8) | 9
Methodology | 1. Built a canonical requirement list from RFQ.csv, KBH 2025 specs.pdf, the legacy Drupal custom modules, and the public legacy site structure. 2. Traced the new Next.js codebase statically across app routes, server modules, components, and payment/auth paths. 3. Ran local evidence checks: pnpm build, pnpm test, DB migrate/seed, and public route smoke probes on a local server. 4. Separated required, optional, withdrawn, and out-of-scope rows so the verdict is based on mandatory feature delivery rather than wishful accounting.
Confidence Limits | Live deployment became available on 2026-04-19 with test credentials for admin/editor/journalist/user/business roles. Public and authenticated read flows, dashboard reachability, organization billing API state, and paywall surfaces were rechecked against the deployed runtime. Stripe settlement, webhook delivery, and destructive admin writes still remain partly code-reviewed because no live provider control or safe write sandbox was supplied.
Evidence Notes | Live runtime checked: https://mkbh-dev.up.railway.app/. Reconfirmed on 2026-04-19: `/api/organization/[id]` allowed read/update by an ordinary user; anonymous `/api/upload/delete` reached delete logic; anonymous `/api/trpc/paywallBypassToken.count/list` and `/paywallBypassIp.count/list` returned live data; `/dashboard/posts/new`, `/dashboard/content/polls/new`, `/dashboard/posts/tags`, `/dashboard/payment`, `/dashboard/config`, `/dashboard/media`, `/dashboard/media/create-many`, `/dashboard/paywall-bypass/tokens`, and `/dashboard/admin/users` returned HTTP 200 to ordinary logged-in users; `/dashboard/admin/users/create` and `/dashboard/paywall-bypass/tokens/create` returned 404; `payment.subscription.upgrade` returned `{}`; `payment.subscription.portal` returned a Stripe billing URL for the personal user but 500 `Stripe customer not found for this user` for business users; `/annoncering` still returned HTTP 500.
Artifacts | Workbook: /Users/qodeboy/Workspace/UpWare/playground/magasinet-kbh/output/pdf/magasinet-kbh-acceptance-audit.xlsx Legacy evidence inputs remain under /Users/qodeboy/Workspace/UpWare/playground/magasinet-kbh/output/pdf/ as CSV/PDF support artifacts from the earlier pass.

## Feature Matrix
Feature Matrix
Canonical capability matrix with parity verdicts and evidence references.
id | area | capability | source_scope | source_refs | legacy_evidence | new_evidence | runtime_check | verdict | scope_modifier | confidence | business_impact | notes
F001 | Backend | API authorization and security policies | RFQ+Repo | RFQ.csv:2; src/app/api/organization/[id]/route.ts:8-136; src/app/api/upload/delete/route.ts:4-32; src/server/modules/paywall-bypass/paywall-bypass-token.router.ts:28-48 | Legacy custom modules enforce admin/editor access patterns across account, paywall, and content flows in mkbh_account_page, mkbh_paywall, mkbh_article_page. | Auth exists, but multiple sensitive paths are under-protected: arbitrary organization read/update by any logged-in user, unauthenticated upload delete, and public paywall-bypass token/IP list/get/count procedures. | Live 2026-04-19: `user@example.com` read and no-op updated the business organization `867b66e2-6d7c-4503-9199-7db6ec75572d` through `/api/organization/[id]`; unauthenticated `DELETE /api/upload/delete?path=...` reached deletion logic and returned 500 instead of 401/403; anonymous and logged-in callers could query `paywallBypassToken.count/list` and `paywallBypassIp.count/list` via `/api/trpc/*` and received live data (`0` / `[]`). | Partial | required | 0.99 | 10 | Security posture is materially below acceptance grade even though auth primitives exist.
F002 | Backend / Users | User accounts: login, registration, profile, and self-management | RFQ+Repo | RFQ.csv:3; RFQ.csv:51; src/server/auth/index.ts:33-135; src/app/(main)/(auth)/_components/sign-up-form.tsx; src/app/(main)/profile/page.tsx | Legacy account handling lives in __legacy/sites/all/modules/custom/mkbh_account_page and public profile/account surfaces on the Drupal site. | Better Auth, sign-in/sign-up flows, profile page, subscription list, and organization selection are implemented in the new app. | Public local route probes confirmed auth entry points render; protected profile routes require session. | Full | required | 0.83 | 8 | Quality issues remain elsewhere, but core user-account capability is present.
F003 | Backend / CMS | Article CMS core: create, edit, publish, and schedule content | RFQ+Repo | RFQ.csv:4-6; src/components/dashboard/post/post-editor.tsx; src/components/dashboard/post/post-form.tsx; src/server/commands/post-publish-scheduled.command.ts | Legacy Drupal editor, content types, and scheduling live in mkbh_article_page and theme overrides. | Dashboard editor, Tiptap content model, post CRUD, and scheduled publish job exist in the Next.js codebase. | Live 2026-04-19: `/dashboard/posts` and `/dashboard/posts/new` rendered for admin, editor, journalist, and even ordinary user sessions; `/dashboard/posts/create` remained 404, so the shipped create entry point is `/dashboard/posts/new`. The create page serialized `mainProfileId` for editor/admin sessions, which confirms authoring UI wiring at runtime. | Full | required | 0.94 | 8 | Core authoring exists; the runtime now proves the editor is deployed, but it is also overexposed to ordinary logged-in users.
F004 | Backend / CMS | Support for public article families: KBH+, city life, city spaces, city housing, opinion, visions, projects, reviews, and photo | RFQ+Legacy+Repo | RFQ.csv:5; src/server/modules/post/types/post-type.enum.ts:1-49; src/app/(main)/kbhplus/page.tsx; src/app/(main)/anmeldelser/page.tsx; src/app/(main)/projekter/page.tsx | Legacy public IA exposes /kbhplus, /byens-rum, /byens-liv, /opinion, /visioner, /projekter, /anmeldelser, /foto on the live Drupal site. | Equivalent public routes and post-type enum values exist in the new app. | Local probes returned HTTP 200 for /kbhplus, /projekter, /anmeldelser, /foto, /opinion, /visioner. | Full | required | 0.90 | 8 | The families exist. Requested taxonomy/menu cleanup is a separate gap.
F005 | Backend / CMS | Static/basic pages CMS | RFQ+Specs+Repo | RFQ.csv:6; KBH 2025 specs.pdf:112-139; src/server/modules/page/page.router.ts; src/app/(main)/about/page.tsx; src/app/(main)/kontakt/page.tsx | Legacy basic pages, member FAQ, contact, and about pages are Drupal node/page surfaces. | New app has page module, page CRUD, and multiple public static pages backed by page content fetches. | Local probes returned HTTP 200 for public page routes such as /nyhedsbrev and /payments/business. /annoncering currently fails at runtime and is tracked separately. | Full | required | 0.79 | 6 | The page framework exists, but specific page surfaces can still be broken.
F006 | Comments | Frontend comments widget with threads and replies | RFQ+Legacy+Repo | RFQ.csv:7; RFQ.csv:37; src/components/shared/comments/comment-thread.tsx; src/server/modules/comment/comment.router.ts; __legacy/sites/all/modules/custom/mkbh_comment/mkbh_comment.module | Legacy site supports threaded comments via mkbh_comment and ajax_comments. | New app includes comment list/create/update/delete, threaded rendering, and reply handling. | Live 2026-04-19: public `comments.list` returned seeded article comments for post `65a560e6-1f60-4f6c-99fd-7ddfb978ab76`, and protected `comments.getUserComments` returned real comment history for `user@example.com` and `admin@example.com`. No seeded reply chain was present, so reply-marker rendering was not directly witnessed. | Full | required | 0.93 | 7 | Live deployment proves the comment data paths. Reply rendering and moderation remain only partly evidenced because the seed data had no threaded replies.
F007 | Comments | Comment notifications and unsubscribe flow | Legacy+Repo | __legacy/sites/all/modules/custom/mkbh_comment/mkbh_comment.module; src/server/modules/comment; src/server/mailer | Legacy comment module includes mail-driven comment interactions and unsubscribe-style behavior. | New code shows likes and CRUD, but no equivalent comment-notification or unsubscribe flow was located. | Live deployment and credentials did not expose any comment-notification or unsubscribe surface, and no mail sink was available to verify delivery. This row remains code-review-only after the runtime pass. | Skipped | required | 0.74 | 5 | Community retention feature from legacy appears missing.
F008 | Analytics | Article metrics: views, shares, reactions, and GA-enriched counts | RFQ+Legacy+Repo | RFQ.csv:8; src/server/modules/analytic/analytic.service.ts:38-168; src/components/shared/google-analytics/google-analytics-stat.tsx:5-20 | Legacy custom analytics module mkbh_node_stats tracked public engagement metrics. | The new app stores view/share/reaction stats and can sum GA views, but dashboard reporting is limited and live proof is incomplete. | Article detail code triggers `analytic.view`; local runtime exercised public article pages successfully. | Partial | required | 0.77 | 6 | Metrics plumbing exists, but acceptance-grade reporting and verification are incomplete.
F009 | Media | Media library, upload workflows, and media CRUD | RFQ+Legacy+Repo | RFQ.csv:9; src/server/modules/media/media.router.ts; src/components/dashboard/media/media-list.tsx; src/components/dashboard/media/media-create-many-form.tsx | Legacy site has custom media flows, photo bulk upload, audio/video players, and inline-image support. | New app ships media CRUD, multi-upload, preview, caption/alt/author fields, and reusable picker flows. | Build and seeded runtime passed. No authenticated browser upload was performed in this pass. | Full | required | 0.81 | 7 | A separate security finding exists for unauthenticated asset deletion.
F010 | Recommender | Related-content or recommender system | RFQ+Legacy+Repo | RFQ.csv:10; src/components/shared/post-sections/related-article.tsx; src/components/shared/post-sections/related-vision.tsx | Legacy site has related-content blocks and article adjacency in mkbh_blocks and mkbh_article_page. | New app renders related content UI blocks, but no AI or richer recommendation logic was evidenced. | Public article templates reference related-content components; no dedicated recommender service was found. | Partial | required | 0.73 | 4 | Baseline related-content UX exists. RFQ hint toward stronger recommender behavior is unmet.
F011 | Map / Geodata | Geocoding, geodatabase, and map-backed content | RFQ+Legacy+Repo | RFQ.csv:11; src/app/(main)/kort/page.tsx; src/server/modules/post/post.router.ts; src/components/tip-tap/tiptap-widgets/map | Legacy site has dedicated map and projects modules backed by map markers and geodata. | The new app exposes a public map page, post geolocation queries, and map widgets, but explicit geocoding workflows were not fully proven. | Local probe of /kort returned HTTP 200. Public rendering works, but the page heading is sparse and deeper map interactions were not manually exercised. | Partial | required | 0.73 | 7 | Public map surface exists. Back-office geocoding fidelity needs authenticated verification.
F012 | Archive | Magazine archive surface and archive management | RFQ+Legacy+Live+Repo | RFQ.csv:12; https://www.magasinetkbh.dk/arkiv; __legacy/sites/all/modules/custom/mkbh_archive_page/mkbh_archive_page.module; src/app/(main)/arkiv/page.tsx:19-179 | Legacy live archive exposes the full historical magazine archive with real issue downloads. | New app replaces the archive with a hardcoded five-row constant that reuses the same image and PDF path while claiming all 57 issues are available. | Local GET /arkiv -> 200 with heading 'bladarkiv'; page text claims all 57 issues, but code only contains five static entries. | Partial | required | 0.96 | 8 | This is one of the clearest acceptance failures and also a mock/hardcode finding.
F013 | Newsletter | Newsletter subscription and management | RFQ+Legacy+Live+Repo | RFQ.csv:13; https://www.magasinetkbh.dk/nyhedsbrev; src/server/modules/newsletter/services/newsletter.service.ts:25-46; src/app/(main)/nyhedsbrev/_components/newsletter-form.tsx:35-39 | Legacy site exposes newsletter capture and management surface on /nyhedsbrev. | Generic newsletter subscribe mutation exists, popup/project widgets call it, but the dedicated newsletter page submit handler is empty and no management UI was found. | Local GET /nyhedsbrev -> 200 with heading 'Modtag vores nyhedsbrev'. The page renders, but its primary form does not call the backend. | Partial | required | 0.96 | 8 | Public-facing newsletter entry point is materially fake.
F014 | Newsletter | RSS feed surface | Legacy+Live+Repo | https://www.magasinetkbh.dk/nyhedsbrev; __legacy/sites/all/modules/custom/mkbh_rss_feed; src/app/(main)/nyhedsbrev/page.tsx:63-83 | Legacy system has a custom RSS feed module and public feed discovery. | New site only links out to an external static XML feed hosted elsewhere; no new in-app RSS generation was found. | Local GET /nyhedsbrev -> 200; RSS section renders a direct external URL. | Partial | required | 0.86 | 4 | Users still get a feed link, but the capability was not migrated into the application itself.
F015 | Payments | Payment processing via Stripe and MobilePay | RFQ+Legacy+Repo | RFQ.csv:14-18; src/server/modules/payment/providers/stripe.provider.ts; src/server/modules/payment/providers/mobilepay.provider.ts | Legacy site used Stripe and MobilePay across member and donation flows. | Both providers exist in the new backend, but adjacent flows remain incomplete or uneven, especially upgrade/self-service and business seat changes on MobilePay. | No end-to-end live payment was run. Public payment pages render locally. | Partial | required | 0.75 | 9 | Core payment providers exist, but acceptance cannot treat the surrounding flow as complete.
F016 | Payments | Recurring billing management and self-service subscription lifecycle | RFQ+Legacy+Repo | RFQ.csv:16; src/components/payment/blocks/subscription-card.tsx:65-211; src/server/modules/payment/services/subscription.service.ts:170-175 | Legacy account pages supported paid-member lifecycle management. | Cancel and restore exist, but upgrade is stubbed and UI still calls it. Portal behavior also degrades to errors or fallbacks. | Live 2026-04-19: `payment.subscription.upgrade` returned empty JSON `{}` for both a real personal subscription (`e7e15246-bb32-44ef-8551-cf136679505b`) and the seeded business subscription (`24ea47e5-ab49-4a8f-8358-a126131485d0`), proving the advertised upgrade path is stubbed in production. `payment.subscription.portal` returned a Stripe billing URL for the personal user but 500 `Stripe customer not found for this user` for business master/employee sessions. | Partial | required | 0.99 | 9 | The most obvious self-service upgrade path is not implemented, and the business portal path is broken on the seeded live subscription state.
F017 | Payments | Business users, seats, invitations, and sub-accounts | RFQ+Legacy+Repo | RFQ.csv:17; src/app/api/organization/dashboard/route.ts:35-227; src/app/api/organization/invitations/route.ts:22-168; src/server/modules/payment/providers/mobilepay.provider.ts:74-76 | Legacy account/business handling supported organization-style memberships and seat concepts. | The new app does implement organization dashboards, invitations, membership lists, and seat adjustment, but the feature is uneven: seat adjustment is unsupported for MobilePay and a separate by-id organization API is insecure. | Feature judged primarily from code because business flows require authenticated state and provider access. | Partial | required | 0.84 | 9 | This is not absent, but it is not cleanly complete enough for an unconditional acceptance.
F018 | Payments | Webhook integration for Stripe and MobilePay | RFQ+Repo | RFQ.csv:18; src/app/api/mobilepay/webhooks/route.ts; src/server/modules/payment/services/mobilepay-webhook-handler.service.ts; src/server/modules/payment/services/stripe-webhook.service.ts | Legacy payment flows relied on webhook-style asynchronous state updates. | Webhook routes and handlers exist for both providers in the new application. | No external provider callbacks were replayed in this audit pass. | Full | required | 0.68 | 6 | Implemented in code, but runtime confidence is lower without provider-side execution.
F019 | Data | Pre-launch data migration | RFQ+Legacy | RFQ.csv:19; __legacy/sites/all/modules/custom/mkbh_migration | Legacy codebase contains migration-related custom tooling. | This audit did not evaluate migrated content/data parity. The new repo includes seeders and schema, but not a validated migration result. | Explicitly excluded from this pass by audit scope. | Skipped | out_of_scope | 0.40 | 5 | Not scored in acceptance verdict for this report.
F020 | Non-functional | SLA / TTLB / deployability expectations | RFQ+Repo | RFQ.csv:20; pnpm build output; pnpm test output | Legacy system at least operates publicly at scale today. | New app builds locally, but default test command is broken, public /annoncering returns 500 locally, and there is no evidence of SLA enforcement or performance budgets. | Local `pnpm build` compiled successfully; local `pnpm test` fails because legacy tests are included; local `/annoncering` returned 500. | Partial | required | 0.94 | 8 | Deployability is better than zero, but not acceptance-clean.
F021 | Dashboard | User management dashboard | RFQ+Repo | RFQ.csv:22-24; src/app/dashboard/auth/users/page.tsx; src/app/dashboard/admin/users/page.tsx:253-258 | Legacy back-office supported user administration via Drupal admin views. | The new app has user management surfaces, but there are duplicate dashboard implementations and at least one broken create-user link under /dashboard/admin/users/create. | Live 2026-04-19: `/dashboard/auth/users` was admin-only, but the duplicate `/dashboard/admin/users` page rendered for user/editor/journalist/business/admin sessions and exposed an `Opret bruger` link to `/dashboard/admin/users/create`, which returned 404 for every tested role. | Partial | required | 0.98 | 7 | Core capability exists, but the shipped dashboard duplicates the user-admin surface, exposes it too broadly, and still links to a dead create route.
F022 | Dashboard | Article management dashboard, writing editor, and custom widget placements | RFQ+Specs+Repo | RFQ.csv:25-27; KBH 2025 specs.pdf:21-74; src/components/tip-tap/components/tiptap-toolbar.tsx; src/components/tip-tap/tiptap-node | Legacy editor supported rich embedded widgets and flexible article layouts. | New dashboard editor is rich and extensible, with inline widget nodes, media selection, poll widgets, map widgets, and metadata forms. | Build passed and seeded content renders widget-aware public pages. Admin-side authoring was assessed from code only. | Full | required | 0.82 | 8 | Several specific widget/taxonomy deltas still fail separately below.
F023 | Dashboard | Reports for users, subscriptions, and business/content metrics | RFQ+Legacy+Repo | RFQ.csv:28-30; src/components/dashboard/dashboard/dashboard-page.tsx:34-119 | Legacy platform had admin/reporting expectations around users, subscriptions, and business metrics. | New dashboard shows simple counts, but no real subscription reporting, churn reporting, or business/content metrics suite matching the RFQ wording was found. | Dashboard metrics were assessed from code only. | Partial | required | 0.80 | 6 | Basic counters exist. Actual reporting depth does not.
F024 | Dashboard | Automated emails | RFQ+Legacy+Repo | RFQ.csv:31-32; src/server/modules/auth/auth.service.ts:149-188; src/server/mailer/templates | Legacy system used automated email behavior in account and community flows. | New app sends auth and invitation emails, but no broader automated email/reporting capability matching the RFQ phrasing was located. | No mail sink or outbound mailbox access was available. The live pass confirmed auth/profile/dashboard surfaces only; automated email breadth still cannot be proved beyond the code paths already reviewed. | Partial | required | 0.75 | 5 | Email infrastructure exists; the promised feature breadth does not.
F025 | Dashboard | CSS injector or admin-controlled dynamic CSS | RFQ+Specs+Legacy+Repo | RFQ.csv:33; KBH 2025 specs.pdf:5-16; src/server/modules/site-config/enums/site-config-key.enum.ts:2; src/app/page.tsx:142-152 | Legacy site had dynamic CSS/front-page variant behavior. | New site only exposes a `homeLayout` switch; no generic CSS injector or equivalent admin CSS control was found. | Live 2026-04-19: `/dashboard/config` rendered for every authenticated role. The shipped page exposed `Generelt`, `Meta-tags`, and `Integrationer` tabs and serialized a `homeLayout` setting, but no CSS injector / stylesheet / custom CSS control was surfaced in the deployment HTML. | Skipped | required | 0.91 | 4 | The narrow homepage layout toggle does not satisfy a CSS injector feature.
F026 | Frontend | Dynamic block templates and grid-based composable front page | RFQ+Legacy+Repo | RFQ.csv:35-41; src/app/page.tsx:33-175; src/app/(main)/_components | Legacy home/section pages used custom block composition. | New homepage is a composed grid of section blocks and most-read/vision/review/map blocks. | Local GET / -> 200 and rendered homepage sections with seeded content. | Full | required | 0.90 | 7 | Composition exists and is publicly reachable.
F027 | Frontend | Manual front-page top-layout variant switch | Specs+Repo | KBH 2025 specs.pdf:5-16; src/app/page.tsx:142-152; src/server/modules/site-config/enums/site-config-key.enum.ts:2 | Legacy site reportedly toggled two homepage variants via dynamic CSS/time-based behavior. | New homepage supports `default` and `compact` layouts via site config, but the spec asked for very easy main-menu access and that UX was not verified. | Code review plus local homepage render. No authenticated dashboard/menu walkthrough available. | Partial | required | 0.76 | 5 | Likely functionally present, but the operational UX requirement is unproven.
F028 | Frontend / Map | Map page and map widget | RFQ+Legacy+Repo | RFQ.csv:42; src/app/(main)/kort/page.tsx; src/config/enums/tip-tap.ts:76-80 | Legacy site had a dedicated map page and map-related widgets/markers. | New app ships a map page and map widget type in the editor. | Local GET /kort -> 200. | Full | required | 0.84 | 7 | Deeper interactive map QA was outside this pass.
F029 | Frontend / Sections | City spaces, city life, and city housing list/detail pages | RFQ+Legacy+Repo | RFQ.csv:43; src/app/(main)/byens-rum/page.tsx; src/app/(main)/byens-liv/page.tsx; src/app/(main)/byens-bolig/page.tsx; src/app/(main)/inhold/[slug]/page.tsx | Legacy public IA includes city-space and city-life section routes and details. | New app implements list pages for those sections and shared detail rendering under the article route. | Local probes returned HTTP 200 for seeded /inhold/* content and city-family list routes render via the homepage and section pages. | Full | required | 0.82 | 7 | Routing defect is covered separately under root-slug migration.
F030 | Frontend / Sections | Opinion list and detail pages | RFQ+Legacy+Repo | RFQ.csv:44; src/app/(main)/opinion/page.tsx; src/app/(main)/opinion/[slug]/page.tsx | Legacy live site exposes opinion list/detail pages. | New app implements opinion list and detail routes. | Local GET /opinion -> 200. | Full | required | 0.87 | 6
F031 | Frontend / Sections | Visions list and detail pages | RFQ+Legacy+Live+Repo | RFQ.csv:45; https://www.magasinetkbh.dk/vision/lav-cykelparkering-over-alle-hovedbanegarden-perroner; src/app/(main)/visioner/page.tsx; src/app/(main)/visioner/[slug]/page.tsx | Legacy site exposes public vision pages with voting/comment context. | New app implements visions list/detail routes and renders vote-related stats. | Local GET /visioner -> 200. | Full | required | 0.83 | 6
F032 | Frontend / Sections | Projects list and detail pages | RFQ+Legacy+Live+Repo | RFQ.csv:46; https://www.magasinetkbh.dk/projekter; https://www.magasinetkbh.dk/projekt/axel-towers; src/app/(main)/projekter/page.tsx; src/app/(main)/projekter/[slug]/page.tsx | Legacy site exposes project index/detail pages and project-specific update calls to action. | New app implements project list/detail routes and project metadata rendering. | Local GET /projekter -> 200. | Full | required | 0.86 | 7 | Project alerting is a separate missing sub-capability.
F033 | Frontend / Sections | Reviews list and detail pages | RFQ+Legacy+Repo | RFQ.csv:47; src/app/(main)/anmeldelser/page.tsx; src/app/(main)/anmeldelser/[slug]/page.tsx | Legacy site exposes reviews and scene/film review metadata. | New app implements review list/detail routes and review metadata fields. | Local GET /anmeldelser -> 200. | Full | required | 0.87 | 6
F034 | Frontend / Sections | Photo list and detail pages | RFQ+Legacy+Repo | RFQ.csv:48; src/app/(main)/foto/page.tsx; src/app/(main)/foto/[slug]/page.tsx | Legacy site exposes public photo series/list surfaces. | New app implements photo list/detail routes and photo media rendering. | Local GET /foto -> 200. | Full | required | 0.86 | 6
F035 | Frontend / Commerce | Personal subscription purchase flow | RFQ+Legacy+Repo | RFQ.csv:49; src/app/(main)/payments/personal/page.tsx; src/app/(main)/payments/personal/checkout/page.tsx | Legacy site offered personal member purchase and support flows. | New app has personal pricing and checkout pages, but surrounding lifecycle is incomplete and the landing page still carries hardcoded marketing values. | Local GET /payments/personal -> 200. Checkout was not executed without authenticated payment testing. | Partial | required | 0.80 | 9 | Core flow exists, but acceptance cannot treat it as fully delivered.
F036 | Frontend / Commerce | Business subscription purchase flow | RFQ+Legacy+Repo | RFQ.csv:49; src/app/(main)/payments/business/page.tsx; src/app/(main)/payments/business/checkout/page.tsx | Legacy site supported organization/business memberships. | New app has business pricing and checkout scaffolding plus organization dashboard flows, but some provider paths and later management actions are incomplete. | Local GET /payments/business -> 200. | Partial | required | 0.82 | 9 | Good amount of code exists, but not enough to call the overall business flow fully accepted.
F037 | Frontend / Commercial | Advertiser promo surface | RFQ+Live+Repo | RFQ.csv:50; src/app/(main)/annoncering/page.tsx; https://www.magasinetkbh.dk/annoncering | Legacy site has a public advertiser information page. | New app has an advertising page route, but it crashes locally with a server-side 500. | Local GET /annoncering -> 500; server log captured `TypeError: a.map is not a function` from the built app. | Partial | required | 0.95 | 7 | Public commercial entry point is currently broken at runtime.
F038 | Frontend / Commercial | Sponsor promo surface | RFQ+Live+Repo | RFQ.csv:50; src/app/(main)/payments/sponsorship/page.tsx; https://www.magasinetkbh.dk/sponsor | Legacy site exposes sponsor information and sponsor-related assets. | New app ships a sponsorship page, sponsor plan CRUD, and sponsor listing, but conversion still relies on mailto/manual contact and legacy assets. | Local GET /payments/sponsorship -> 200. | Partial | required | 0.90 | 6 | Usable as a brochure page, not as a fully modernized flow.
F039 | Frontend / Profile | User profile and subscription self-management | RFQ+Repo | RFQ.csv:51; src/app/(main)/profile/page.tsx; src/components/profile/blocks/subscription-list.tsx | Legacy account page handled profile and membership management. | New app includes profile area, subscription cards, invoices, organization list, and comment history. | Protected routes were validated by code review. Public probes confirmed profile entry points exist in the route tree. | Full | required | 0.77 | 7 | Subscription upgrade remains incomplete, but the broader profile surface exists.
F040 | Frontend / Taxonomy | Author, district, and tag index pages | RFQ+Legacy+Live+Repo | RFQ.csv:52; https://www.magasinetkbh.dk/search/node/metro; src/app/(main)/bydel/[slug]/page.tsx; src/app/(main)/emne/[slug]/page.tsx; src/app/(main)/skribent/[slug]/page.tsx | Legacy public site exposes taxonomy and author-style landing pages. | District and tag routes clearly exist and render. Author route exists in code, but live proof was limited because seeded author data was sparse. | Local GET /bydel/indre-by -> 200; local GET /emne/metro -> 200; local probe of a synthetic author slug returned 404. | Partial | required | 0.78 | 5 | Route infrastructure is present; author-page confidence is lower without seeded author data.
F041 | Paywall | SEO-friendly paywall and gated KBH+ behavior | RFQ+Legacy+Repo | RFQ.csv:39; src/components/paywall/kbhplus-paywall.tsx; src/server/modules/auth/auth.service.ts:73-127 | Legacy site used paywall logic and subscription-aware access controls. | New app has KBH+ gating and subscription checks, but paywall bypass exposure and guest-link weaknesses materially undermine the implementation. | Seeded KBH+ route rendered publicly; authenticated subscription gating was assessed from code only. | Partial | required | 0.80 | 9 | Feature exists, but the control surface is not safely implemented.
F042 | Widgets | Inline timeline widget | Specs+Repo | KBH 2025 specs.pdf:21-39; src/components/tip-tap/types/types.ts:12-27; src/components/tip-tap/tiptap-node/timeline/timeline-node.tsx | Legacy editor did not expose this exact new widget; it was a spec delta. | The new editor stores title, description, timeline items, icon, media, and text, matching the requested shape. | No authored timeline example or interactive editor browser was available on the deployment. This row still rests on shipped code review rather than direct live editing. | Full | required | 0.88 | 5
F043 | Widgets | Inline chart widget with editorial data entry | Specs+Repo | KBH 2025 specs.pdf:40-48; src/config/enums/tip-tap.ts:55-117 | This was a net-new requirement. | The new editor exposes poll, vote, suggestion, timeline, map, etc., but no generic chart widget type or chart-data-entry workflow was found. | Live 2026-04-19: `/dashboard/content/polls` and `/dashboard/content/polls/new` rendered in the deployment, but no separate generic chart-authoring surface or chart-widget configuration was exposed. The chart-widget absence remains mostly code-reviewed. | Skipped | required | 0.93 | 6 | Existing chart components are tied to poll result rendering, not a generic inline chart authoring feature.
F044 | Widgets | Inline poll widget with multiple choice, checkboxes, slider, and free text | Specs+Repo | KBH 2025 specs.pdf:51-61; src/server/modules/poll/types/poll-question-type.enum.ts:1-16; src/components/form/control/poll-question.collection.tsx:46-71 | This was a new requirement over legacy. | The editor and poll model support radio, checkbox, slider, and textarea question types. | Live 2026-04-19: `/dashboard/content/polls` and `/dashboard/content/polls/new` rendered for user/editor/admin sessions, confirming that the poll management surface is actually deployed. The exact question-type breadth still comes from code review because the create form is client-rendered and not fully enumerated in SSR HTML. | Full | required | 0.93 | 5
F045 | Widgets | Inline CityChange single-suggestion widget with ID field and address override | Specs+Repo | KBH 2025 specs.pdf:63-74; src/components/tip-tap/tiptap-node/suggestions/suggestions-node.tsx:37-169; src/components/tip-tap/types/types.ts:76-79 | The spec originally asked for this as new functionality. | The editor supports a suggestion ID and variant, but no address-override field exists. | No authored suggestion-widget example was present in seeded content and the editor control was not safely exercised live. The missing address-override field still rests on code review. | Partial | withdrawn | 0.89 | 3 | Withdrawn from pass/fail scoring because the spec later deletes this as net-new scope.
F046 | Widgets | Before/after slider 1px white split stroke | Specs+Repo | KBH 2025 specs.pdf:81-85; src/components/tip-tap/tiptap-widgets/before-after-image/before-after-image.tsx:96-103 | Legacy had a before/after slider; spec asked for a styling tweak. | The slider renders a white split line (`w-1 bg-white`) and draggable handle. | Live deployment bundle loaded by `/dashboard/posts/new` contained the before/after editor copy `Vælg før/efter billeder`, `Før-billede etiket`, `Efter-billede etiket`, `Billedtekst`, and `Forfatter`, which matches the shipped widget configuration surface. | Full | required | 0.93 | 3
F047 | Editorial taxonomy | Global tag replace / merge workflow | Specs+Repo | KBH 2025 specs.pdf:88-97; src/server/modules/tag; src/components/dashboard/tag | Legacy editorial workflow explicitly needed tag cleanup/merge ability. | New tag CRUD exists, but no tag replace/merge flow across articles was found. | Live 2026-04-19: `/dashboard/posts/tags` rendered for user/editor/admin sessions and exposed `Nyt tag`, `Opret tag`, `Rediger`, `Slet`, `Slug`, and `Anvendelse`. No replace/merge action surfaced on the deployed tag management page. | Skipped | required | 0.95 | 5
F048 | Editorial taxonomy | Improved multi-tag add UX | Specs+Repo | KBH 2025 specs.pdf:100-108; src/components/form/control/tag.collection.tsx:135-167 | This was a requested editorial UX improvement. | Selected tags are maintained separately from search results and the picker clears search state on close, matching the intended flow substantially better than legacy. | The live post-create route exists, but the multi-tag picker interaction is client-side and was not driven end-to-end in this pass. This row remains largely source-backed after the runtime review. | Full | required | 0.84 | 3
F049 | Editorial model | Reworked article-type taxonomy and creation menu | Specs+Repo | KBH 2025 specs.pdf:112-139; src/server/modules/post/types/post-type.enum.ts:1-49; src/components/dashboard/post/post-sidebar-form.tsx:106-123 | Legacy taxonomy and menu structure were explicitly called illogical and needed restructuring. | New app still exposes a flat topic enum. Several requested distinctions such as Standard-with-review, sponsored as type, and richer hierarchy/menu semantics are not present as specified. | Live deployment HTML for `/dashboard/posts/new` serialized a flat type map: `kbhplus`, `foto`, `opinion`, `visioner`, `byens-rum`, `byens-liv`, `byens-bolig`, `projekter`, `anmeldelser`. Requested richer hierarchy distinctions such as sponsored-as-type are not present in the shipped create form. | Partial | required | 0.96 | 6 | The platform supports the public families, but the shipped editorial creation model is still the same flat taxonomy the spec explicitly asked to clean up.
F050 | Editorial model | Primary topic tag behavior with frontend display and quote icon for 'kommentar' | Specs+Repo | KBH 2025 specs.pdf:141-159; src/components/shared/post-tag.tsx:30-34; src/components/dashboard/post/post-sidebar-form.tsx:162-164 | This is a spec delta modeled on legacy pretitle behavior. | Primary tag exists in the editor, renders on frontend, links to tag pages, and adds a quote icon when the tag name is `kommentar`. | Local homepage/article rendering plus code review support this. | Full | required | 0.90 | 4
F051 | Editorial UX | Special-character shortcut buttons in editor for em-dash and guillemets | Specs+Repo | KBH 2025 specs.pdf:164-172; src/components/tip-tap/components/tiptap-toolbar.tsx:132-260 | This was a new editorial convenience requirement. | Toolbar buttons exist for formatting, alignment, lists, links, etc., but no explicit shortcut buttons for `—`, `»`, or `«` were found. | Live bundle/HTML search on `/dashboard/posts/new` did not surface any dedicated `—`, `»`, or `«` editor shortcut controls. This remains primarily a code-review absence, but the deployed editor output provided no contrary evidence. | Skipped | required | 0.92 | 3
F052 | Routing / SEO | Root-slug article URLs plus redirects from old article paths | Specs+Live+Repo | KBH 2025 specs.pdf:174-179; https://www.magasinetkbh.dk/search/node/metro; src/config/routes.ts:10-18; src/app/(main)/inhold/[slug]/page.tsx:21-83; src/middleware.ts | Legacy site used `/indhold/...`; spec requested root-slug URLs with redirects. | New app still routes many article families under `/inhold/${slug}` instead of root slugs, and no redirect implementation for the old scheme was found. | Local seeded article probe /inhold/byens-kulturelle-liv -> 200. | Skipped | required | 0.95 | 8 | This is both a spec miss and a migration/SEO miss.
F053 | Editorial media | Bulk-fill photographer and ALT fields for inline images | Specs+Legacy+Repo | KBH 2025 specs.pdf:182-188; __legacy/sites/all/modules/custom/mkbh_photo_series_bulk_upload; src/components/dashboard/media/media-create-many-form.tsx:61-137; src/components/tip-tap/tiptap-node/inline-image/inline-image-modal.tsx:198-229 | Legacy had dedicated photo bulk-upload tooling and the spec asked for mass-populate behavior. | New app lets editors edit alt/caption/author per image, but no one-shot bulk-populate action for all selected images was found. | Live 2026-04-19: `/dashboard/media/create-many` rendered a real mass-upload screen (`Upload flere mediefiler på én gang`) and the deployed media/editor copy exposed per-item `Forfatter`, `Billedtekst`, and `Alt-tekst` fields. No apply-to-all / one-shot bulk-populate control surfaced in the deployed HTML. | Skipped | required | 0.93 | 5
F054 | Editorial media | Thumbnail-based inline-image placement in the editor | Specs+Repo | KBH 2025 specs.pdf:189-191; src/components/tip-tap/tiptap-node/inline-image/inline-image-node.tsx:57-93; src/components/tip-tap/tiptap-node/inline-image/inline-image-modal.tsx:204-210 | Legacy editor used opaque inline-image tokens; spec asked for thumbnail placement. | New editor renders selected images as visible previews/thumbnails inside the node UI. | Live deployment bundle for `/dashboard/posts/new` exposed inline-image editor actions `Vælg billede`, `Tilføj billede`, and `* Stryg til venstre for at se alle valgte billeder →`, which is consistent with thumbnail/preview-based inline-image placement. | Full | required | 0.93 | 4
F055 | Editorial media | Drag-and-drop reordering of inline-image placeholders | Specs+Repo | KBH 2025 specs.pdf:192-193; src/components/tip-tap/tiptap-node/inline-image/inline-image-modal.tsx | Spec marked this as a nice-to-have. | No drag-and-drop ordering UI for inline-image placeholders was found in the modal or node. | Live deployment bundle exposed multi-image guidance (`Stryg til venstre ...`), but no drag/drop or reorder affordance surfaced on the shipped editor pages. | Skipped | optional | 0.89 | 2 | Kept in appendix scoring only; does not drive refund on its own.
F056 | Editorial media | Edit inline-image captions directly from the thumbnail UI | Specs+Repo | KBH 2025 specs.pdf:194-197; src/components/tip-tap/tiptap-node/inline-image/inline-image-modal.tsx:219-229 | Spec marked this as nice-to-have if UX was good. | Caption fields are editable directly in the inline-image modal alongside the thumbnail preview. | Live deployment bundle for `/dashboard/posts/new` exposed inline image/media caption and author copy (`Billedtekst`, `Forfatter`, `Alt-tekst`) alongside the image-widget configuration strings. The specific modal interaction was not executed, but the shipped bundle matches the implemented caption-edit surface. | Full | optional | 0.9 | 2 | Optional item; implemented.
F057 | Editorial UX | Pre-populate writer/byline from the creating user | Specs+Repo | KBH 2025 specs.pdf:200-205; src/components/dashboard/post/post-editor.tsx:191-206 | This was an editorial productivity requirement. | New post defaults `authorId` to the main profile of the creating user while keeping the field editable. | Live 2026-04-19: `/dashboard/posts/new` serialized `mainProfileId` for editor and admin sessions (`914981d4-cd0f-4730-80a9-c352d3c6c812`, `0a336512-bbf2-4782-a32a-dd5888947584`) and left it undefined for a plain user, which matches the intended byline prefill from the creator's main profile. | Full | required | 0.95 | 3
F058 | Search | AND semantics for multi-term search | Specs+Live+Repo | KBH 2025 specs.pdf:208-212; https://www.magasinetkbh.dk/search/node/metro; src/server/modules/post/repositories/post.repository.ts:381-384 | Legacy search behavior used OR and the spec explicitly asked to change it. | New search repository still uses `or(ilike(title), ilike(description))`, so the requested AND semantics were not implemented. | Local GET /search?s=test -> 200. Semantics assessed from repository code. | Partial | required | 0.94 | 5 | Feature exists, but the required semantic change does not.
F059 | Design system | Reuse Caecilia and Montserrat fonts from the old site | Specs+Legacy+Repo | KBH 2025 specs.pdf:213-221; __legacy/sites/all/themes/custom/mkbh/assets/fonts; src/lib/utils/font.ts:7-37; src/components/tip-tap/components/text-style-control.tsx:54-60 | Legacy theme ships Caecilia and Montserrat assets. | New app imports local Caecilia files and Montserrat via next/font, and editor font controls expose both. | Live deployment preloaded local Caecilia `.woff2` assets in page HTML and rendered body classes carrying both the Montserrat and Caecilia font modules on dashboard pages. | Full | required | 0.94 | 2
F060 | Design system | Use additional 'Publish' title font pre-launch | Specs | KBH 2025 specs.pdf:219-221 | Originally floated as an extra font change in the spec PDF. | The same spec explicitly marks this as removed. | Not scored. | Skipped | withdrawn | 0.90 | 1 | Withdrawn requirement; excluded from pass/fail scoring.
F061 | CityChange | Deep links from CityChange suggestions into the app | Specs+Repo | KBH 2025 specs.pdf:224-250; src/components/tip-tap/tiptap-widgets/suggestion/suggestion-widget.tsx:227-273 | Legacy/live widget existed already; spec asked only for deep-link enrichment. | The existing location-based suggestion widget now builds the requested `citychange.page.link` deep links per suggestion ID. | No seeded article using the CityChange suggestion widget was available for direct deep-link inspection, and no new content was authored just to prove it. This row remains based on source review after the runtime pass. | Full | required | 0.90 | 3
F062 | Paywall | Guest/share links that bypass the paywall | Specs+Repo | KBH 2025 specs.pdf:252-286; src/components/dashboard/post/post-guest-link-dialog.tsx:17-66; src/components/dashboard/paywall-bypass-token/paywall-bypass-token-list.tsx:63-69 | Spec asked for one-time and time-window guest links. | New app can mint tokens with optional expiry, but it does not implement one-time invalidation, list/edit UI is broken, and URL generation is wrong for `/inhold/*` content. | Live 2026-04-19: any logged-in role could load `/dashboard/paywall-bypass/tokens`, while the backing `paywallBypassToken.count/list` procedures also answered to anonymous callers (`0` / `[]`). The dedicated create route `/dashboard/paywall-bypass/tokens/create` returned 404, so the guest-link/admin tooling is still only partially present at runtime. | Partial | required | 0.97 | 8 | Feature exists in reduced and unsafe form.
F063 | Profile | Profile page list of the user's comments with deep link and reply marker | Specs+Repo | KBH 2025 specs.pdf:287-296; src/app/(main)/profile/_components/blocks/comments-block.tsx:25-131; src/components/shared/comments/comment-thread.tsx:19-116 | This was added late in the spec. | New profile comments block lists user comments, marks replies, and links to the specific comment highlight on the article page. | Live 2026-04-19: protected `comments.getUserComments` returned real comment history with post title/topic/slug for `user@example.com` and `admin@example.com`, confirming the profile-comments data path. The seeded data did not include reply comments, so the reply marker itself was not directly witnessed. | Full | required | 0.95 | 4
F064 | Payments | Admin control to pause all subscriber payments while preserving access | Specs+Repo | KBH 2025 specs.pdf:287-341; src/server/modules/payment; src/app/dashboard/payment | Spec explicitly asked for a pause-all-payments admin control across Stripe and MobilePay handling. | No pause-all-subscriber control, service, or admin surface matching this requirement was found. | Live 2026-04-19: `/dashboard/payment` rendered for every authenticated role and described only plan-description editing (`Pricing is managed separately in the Stripe dashboard`). No pause/pause-all subscriber control or wording appeared in the deployed page HTML. | Skipped | required | 0.95 | 8
F065 | Projects | Project-specific update alerts / email notifications | Legacy+Repo | https://www.magasinetkbh.dk/projekt/axel-towers; src/components/shared/post-newsletter-form.tsx:61-89; src/server/modules/newsletter/services/newsletter.service.ts:25-37 | Legacy project detail pages advertise update email alerts. | The new CTA text promises project-specific alerts, but the handler only subscribes the email to the generic newsletter list and sends no project context. | Project CTA is present in article templates; behavior assessed from code. | Skipped | required | 0.96 | 7 | This is a deceptive mismatch between copy and implementation.
F066 | Dashboard | Paywall-bypass admin UI integrity | Legacy+Repo | __legacy/sites/all/modules/custom/mkbh_paywall; src/components/dashboard/paywall-bypass-token/paywall-bypass-token-list.tsx:111-142; src/components/dashboard/paywall-bypass-token/paywall-bypass-token-editor.tsx:38-79; src/app/dashboard/paywall-bypass/tokens/page.tsx | Legacy paywall bypass/admin utilities existed in custom paywall tooling. | New app has token and IP list UIs, but token edit routes are missing and the token editor binds `expireAt` instead of `expiresAt`. | Live 2026-04-19: `/dashboard/paywall-bypass/tokens` rendered for user/editor/business/admin sessions even though the user version dehydrated `gate.can` as `false`. The page still hydrated successful token `count`/`list` queries, and the related create route returned 404. | Partial | required | 0.99 | 7 | Admin tooling exists, but the live route is both overexposed and internally incomplete.

## Audit Findings
Audit Findings
Ranked security, availability, performance, and engineering-quality findings.
id | category | title | impact_1_10 | reachable | evidence | why_it_matters | recommendation
A001 | Security | Tracked secrets and third-party credentials are committed in `.env.example` | 10 | Repo-wide | .env.example:29-30, 38-39, 62-63, 75-87, 106-107 include real-looking Better Auth, SMTP host, Google, Facebook, Stripe, and MobilePay credentials. | This is direct credential exposure in a deliverable repository. Even if some keys are test-only, it normalizes unsafe handling and exposes integration surface details that do not belong in versioned examples. | Rotate every exposed secret, purge them from history if possible, and replace the example file with placeholders only.
A002 | Security | Paywall-bypass tokens and bypass IPs are publicly enumerable through tRPC | 10 | Reachable to any client that can call public procedures | src/server/modules/paywall-bypass/paywall-bypass-token.router.ts:28-48 and paywall-bypass-ip.router.ts:28-48 expose get/list/count as `publicProcedure`; corresponding services at token.service.ts:66-84 and ip.service.ts:61-79 do not authorize access. Live 2026-04-19: anonymous GETs to `/api/trpc/paywallBypassToken.count`, `/api/trpc/paywallBypassToken.list`, `/api/trpc/paywallBypassIp.count`, and `/api/trpc/paywallBypassIp.list` returned HTTP 200 with live data (`0` / `[]`) when called with valid tRPC input payloads. | This turns paywall exception data into public metadata. It undermines the access-control model and exposes operational bypass mechanisms that should be tightly restricted. | Change list/get/count to protected admin-only procedures and enforce gate authorization in the service layer.
A003 | Security | Any authenticated user can read and update arbitrary organizations by ID | 10 | Reachable to any logged-in user | src/app/api/organization/[id]/route.ts:8-50 performs only a session check before returning org data; PUT at lines 68-122 updates by raw organization ID with no membership or role check. Live 2026-04-19: `user@example.com` successfully read business organization `867b66e2-6d7c-4503-9199-7db6ec75572d` and performed a no-op PUT update against the same record, changing only `updatedAt`. | This is a read/write insecure direct object reference on organization data. It exposes and allows modification of another organization's profile details with nothing more than a valid session. | Require membership/role checks before GET and PUT, and route these operations through a single authorized service instead of raw table access.
A004 | Security | Unauthenticated upload-delete endpoint can delete assets by path or ID | 9 | Public API surface | src/app/api/upload/delete/route.ts:4-32 accepts DELETE with a `path` query parameter and calls deleteAsset; src/lib/utils/upload-utils.ts:24-33 passes the identifier straight to `nup.deleteAsset`. Live 2026-04-19: anonymous `DELETE /api/upload/delete?path=definitely-not-a-real-file-for-audit.txt` returned HTTP 500 `{"error":"Failed to delete file"}` instead of 401/403, proving the unauthenticated delete path is reachable. | This is an obvious availability and integrity problem. Any caller that can guess or discover an asset path can attempt deletion without authentication. | Require authentication and ownership/permission checks before deletion. Prefer signed, short-lived deletion intents rather than raw public file-path deletion.
A005 | Engineering quality | Public `/test-stripe` demo page ships in the deliverable | 9 | Public route | src/app/test-stripe/page.tsx:8-195 ships a public Stripe test dashboard that attempts subscription upgrades, organization creation, and organization listing. Live GET `https://mkbh-dev.up.railway.app/test-stripe` returned HTTP 200 on 2026-04-19. | A public demo/test route on a production magazine codebase is not a harmless leftover. It exposes non-customer flows, confuses acceptance testing, and increases attack surface. | Remove the route from production code or lock it behind an internal-only environment gate.
A006 | Engineering quality | Core subscription upgrade path is stubbed while the UI still advertises it | 9 | Authenticated users | src/server/modules/payment/services/subscription.service.ts:170-175 leaves `upgrade()` as TODO and returns `{}`; src/components/payment/blocks/subscription-card.tsx:144-151 still calls it. Live 2026-04-19: POST `/api/trpc/payment.subscription.upgrade` returned `{"result":{"data":{"json":{}}}}` for both the personal subscription `e7e15246-bb32-44ef-8551-cf136679505b` and the seeded business subscription `24ea47e5-ab49-4a8f-8358-a126131485d0`. | This is not a minor defect. It is an acceptance-critical commerce flow presented as if it works. | Implement upgrade end-to-end or remove/disable the UI until it exists.
A007 | Engineering quality | Default test command is broken by vendored legacy tests | 7 | Repo-wide | package.json:39 defines `test` as `vitest run`; local `pnpm test` fails on `__legacy` suites such as beerslider, googleanalytics, jquery-match-height, and Drupal views tests. | A deliverable that cannot pass its default test command without manual scoping is not cleanly maintainable or CI-ready. | Exclude `__legacy` from Vitest, or scope tests to the new app explicitly and add that configuration to the repo.
A008 | Availability | Public advertiser page crashes at runtime | 7 | Public route | Live GET https://mkbh-dev.up.railway.app/annoncering returned HTTP 500 on 2026-04-19 and fell into the Next.js error shell. The same route also failed locally during the earlier review, pointing to a deterministic application bug rather than a local-only artifact. | This is a public-facing commercial page. If the contractor claimed the site was ready, a deterministic runtime 500 on a public route is an acceptance blocker. | Fix the content-shape assumption in the advertising page renderer and add route smoke tests for all public landing pages.
A009 | Performance | Homepage and article routes do heavy server work without evidence of caching discipline | 5 | Public routes | src/app/page.tsx:38-118 fires eleven server fetches for the homepage; article pages such as src/app/(main)/inhold/[slug]/page.tsx:47-66 fetch content and trigger analytics on render. | The code may work at low volume, but it leaves too much expensive server work on hot public routes without visible acceptance evidence for caching or performance budgets. | Add explicit caching strategy, route-level performance budgets, and smoke benchmarks for the homepage and article detail routes.
A010 | Security / Quality | Auth configuration still contains demo/test-only values | 4 | Repo-wide | src/server/auth/index.ts:101 trusts provider `demo-app`; src/server/auth/index.ts:473-480 injects `dd: "test"` into the session payload. | These are not catastrophic on their own, but they are classic signs of unfinished or non-production auth hardening. | Remove demo-only trusted providers and test payload fields before acceptance.
A011 | Engineering quality | Next.js middleware convention is deprecated in the current framework version | 3 | Build-time | Local `pnpm build` emitted `The "middleware" file convention is deprecated. Please use "proxy" instead.`; repo uses src/middleware.ts:1-52. Official Next.js 16.1.5 docs confirm `middleware` is deprecated and renamed to `proxy`. | This is not a business-critical defect, but it is a clear sign the contractor did not finish framework hygiene on a modern stack they chose themselves. | Run the official Next.js middleware-to-proxy migration and update the file/export convention.
A012 | Security / Ops | Public health endpoint reveals uptime, environment, version, and database state | 3 | Public route | src/app/api/health/route.ts:4-55 returns environment, uptime, version, and database connectivity status to any caller. Live 2026-04-19: GET `/api/health` returned `{"status":"healthy","timestamp":"2026-04-19T11:22:37.316Z","uptime":100740.753270731,"environment":"production","version":"1.0.0","database":"connected"}`. | Health checks are useful, but this version discloses more operational detail than necessary for a public website. | Restrict detailed health data to internal callers or return a minimal boolean/liveness response publicly.
A013 | Release engineering | App startup hard-requires Stripe and MobilePay env vars even outside payment flows | 9 | Startup / deploy-time | src/config/env.ts:62-84 makes Stripe and MobilePay variables mandatory during env validation; src/server/auth/index.ts:221-252 registers the Better Auth Stripe integration unconditionally and reads plans from the database. | This blocks minimal bootstraps and makes the app non-portable across environments that only need core web/database/storage services. A release candidate should not refuse to start just because optional payment credentials are absent. | Make payment providers truly optional at startup: gate env validation and provider/plugin registration behind explicit feature flags, and only initialize Stripe/MobilePay when those integrations are enabled.
A014 | Ops / Data safety | Default `pnpm db:seed` command is destructive demo seeding, not production bootstrap | 10 | Repo-wide | package.json:24 exposes `db:seed`; src/server/commands/db-seed.command.ts:35-95 starts by calling clearAllSeeder; src/lib/database/seeders/clear-all-seeder.ts:14-26 deletes existing comments, tags, memberships, invitations, and organizations before the script creates demo users/content. | This is a release blocker because the repo's primary seed command is unsafe on a real environment and mixes destructive wipes with demo fixture creation. Running the wrong documented bootstrap step can destroy data and pollute production with test content. | Split seeding into clearly named commands: a non-destructive, idempotent production bootstrap for required system records, and a separate demo/dev seed. Hard-fail the demo seed in production environments.
A015 | Release engineering | Fresh databases are incomplete after migrations and require manual Stripe sync plus destructive seed paths | 9 | Startup / bootstrap | package.json:30 wires Stripe sync to a separate `stripe:fetch-plans` command; src/server/commands/payment/stripe-fetch-plans.command.ts:1-15 manually runs `syncAllProducts()` and `syncAllPrices()`; src/server/modules/payment/services/stripe.service.ts:33-50 fetches products/prices from Stripe, while src/server/auth/index.ts:239-252 expects active prices to already exist in the database; src/server/database/seeders/payment-plan.seeder.ts:210-219 skips missing plans, and src/server/database/seeders/payment-price.seeder.ts:102-117 only updates rows that already exist. | A clean database is not release-ready after migrations alone. Checkout plan resolution depends on Stripe-backed plan/price rows being present, but the repo provides no safe, idempotent production bootstrap for that catalog or for required content/admin scaffolding. | Automate plan and price reconciliation as part of startup or a dedicated idempotent production bootstrap, and keep the mapping driven from live Stripe product metadata instead of contractor-specific preloaded rows. Add a separate non-destructive bootstrap for required pages, blocks, and admin state.
A016 | Release engineering | Deployment tooling mixes dev-only mounts, fake production tags, and machine-specific compose files | 8 | Repo-wide | docker-compose.yml:28-31 and 43-55 still use `:dev` image tags and bind mounts; docker-compose.yml:93-99 mounts source and env files directly into the running container; Makefile:189-198 pushes a Swarm-style `docker stack deploy` path; infrastructure/docker/docker-compose.yml:9-10,42-43,69-72 hardcodes another developer's local filesystem. | This is not a cosmetic cleanup issue. It signals that the deployment story is fragmented and partly non-portable, which increases the chance that the accepted deployment path is undocumented, unreproducible, or simply not the one checked into the repo. | Separate development and production orchestration cleanly, remove bind mounts and `:dev` tags from release definitions, delete or template machine-specific compose files, and document one reproducible deployment path that actually matches the target platform.
A017 | Security / Release engineering | Mailchimp config is split between env and database, and the DB-backed secret path is publicly readable | 9 | Public tRPC + runtime + scheduled jobs | src/server/modules/site-config/router/index.ts:7-13 exposes `values` as `publicProcedure`; src/server/modules/site-config/services/site-config.service.ts:21-31 returns the full config map; src/server/modules/site-config/validators/site-config.validator.ts:10-12 includes `MAILCHIMP_API_KEY` and `MAILCHIMP_LIST_ID`; src/components/dashboard/site-config/config-editor.tsx:579-590 writes those values through the admin UI; meanwhile src/server/modules/newsletter/services/newsletter.service.ts:17-21 still defaults the newsletter list ID from env, while src/server/clients/mailchimp/mailchimp.service.ts:16-19 and src/lib/mailchimp/client.ts:6-12 read the API key from site-config; src/server/commands/site-config-update-stats.command.ts:20-35 also reads the list ID from site-config and requires an admin user. Live 2026-04-19: anonymous GET `/api/trpc/siteConfig.values` returned HTTP 200, and every authenticated role could load `/dashboard/config`, proving the site-config surface is publicly reachable even when this seed runtime held no stored values. | This is worse than ordinary config drift. The repo creates two competing Mailchimp configuration paths, and the one stored in the database is exposed through a public query if operators use the dashboard for secret storage. | Remove secrets from public site-config entirely, split secret config from public metadata config, and enforce one authoritative Mailchimp configuration path for app and job runtime.
A018 | Data integrity / Analytics | Google Analytics sync injects hardcoded fake page-view data | 8 | Analytics sync command | src/server/clients/google-analytics.service.ts:66-104 appends `result.set('/kort/test', 1000)` after the real GA report loop; src/server/commands/update-ga-page-views.command.ts:11-24 persists every returned path into analytic views. | This poisons the analytics dataset with fabricated rows and proves the sync path is not trustworthy for acceptance, reporting, or business decisions. | Delete the hardcoded test record, quarantine analytics fixtures to test-only code, and add a regression test that rejects unknown synthetic paths in production syncs.
A019 | Release engineering / Analytics | GA credentials are wired as a file-path assumption rather than a deploy-safe secret input | 8 | Build and runtime configuration | src/server/clients/google-analytics.service.ts:15-19 constructs `BetaAnalyticsDataClient()` with default ADC behavior; src/config/env.ts:90-93 exposes only `GOOGLE_APPLICATION_CREDENTIALS`; .env.example:70 points that variable at `/ga-service-account.json`; docker-compose.dev.yml:108-110 passes the path through. Repo search of tracked deploy files found no credential JSON mount or copy beyond that env reference. | The deployment depends on an undocumented credential file appearing inside the runtime container. That is brittle, hard to reproduce, and not encoded in the checked-in deployment path. | Support env-injected JSON credentials or workload identity, and fail bootstrap with an explicit validation error if the analytics auth mechanism is incomplete.
A020 | Release engineering / Payments | Business Stripe checkout customization is effectively unreachable because runtime keys off UUID plan names | 9 | Checkout, sync, and subscription update flows | src/server/auth/index.ts:239-250 exports Better Auth plans with `name: price.id`; src/server/modules/payment/providers/stripe.provider.ts:22-29 purchases with `plan: price.id`; src/server/modules/payment/tables/plan-price.table.ts:20-26 defines that ID as a UUID; src/server/auth/index.ts:268-282 then tests `plan.name.includes('business')` and `plan.name.includes('annual')` to decide business seat pricing and annual behavior. Sync is still brittle too: src/server/modules/payment/services/stripe.service.ts:54-61 falls back from `metadata.type` to `productData.name.includes('business')`, despite metadata already being modeled in src/server/modules/payment/tables/plan.table.ts:17-25 and src/server/modules/payment/types/plan-metadata.type.ts:1-6. Live 2026-04-19: /payments/business serialized the business price records with empty `name`/`description` fields and rendered only naked tariffs (`Fra 59,-`, `Fra 49,-`), which is the deployed symptom of that split identity model. | The business-only Stripe branch that should set seat-based pricing, billing metadata, tax ID collection, and address requirements cannot be trusted when the decisive field is a UUID-shaped price ID. The catalog may sync, but the runtime logic still depends on label heuristics and dead assumptions. | Make Stripe metadata authoritative end-to-end, pass stable typed identifiers instead of UUID-as-name conventions, and delete all name-based business/annual branching from sync and checkout logic.
A021 | Release engineering / Runtime | Every runtime container and scheduled job runs migrations on boot | 8 | Container startup and cron jobs | Dockerfile:115-117 sets `docker-entrypoint.sh` for runtime containers; infrastructure/docker/common/docker-entrypoint.sh:66-76 and 104-119 always wait for DB and run `node migrate.js` before the requested command; docker-compose.dev.yml:134-195 defines scheduled job services with the same image and entrypoint pattern. | App replicas, one-off jobs, and cron tasks all become implicit migration runners. That creates avoidable startup coupling, migration races, and failure modes where an unrelated job cannot run because schema migration behavior changed. | Move schema migration to an explicit one-shot deploy step and keep app and job containers focused on their actual command.
A022 | Security / Ops | Migration script logs the full database connection string | 7 | Migration logs | migrate.js:27-34 prints debug state and then logs `Connection string value:` followed by the raw connection string. | That leaks database credentials into CI, container, or platform logs. It is careless at best and operationally unsafe in any shared logging environment. | Redact secrets in migration logging and keep only non-sensitive connection diagnostics such as host classification or presence checks.
A023 | Release engineering | Checked-in bootstrap scripts are local-dev oriented, partially broken, and seed localhost content | 8 | Repository bootstrap path | infrastructure/seed_db.sh:135-145 checks for non-existent `src/lib/database/seed.ts` and tells operators to run missing `./infrastructure/setup_docker.sh`; infrastructure/setup_env.sh:64-132 generates a localhost-only `.env.local`; infrastructure/seed_db.sh:179-195 advertises seeded demo accounts and localhost services; src/server/database/seeders/page.seeder.ts:755-763 hardcodes `http://localhost:3000/faq` into seeded page content. | The documented bootstrap path is not production-ready. It is misleading, partly broken, and it injects developer URLs and demo assumptions into the dataset that would be unacceptable in a real environment. | Split dev bootstrap from production bootstrap, fix the broken script references, remove localhost URLs from seeded content, and make base content creation idempotent and environment-aware.
A024 | Engineering quality / Admin tooling | The dashboard 'Google' integration UI does not control the actual analytics integration | 6 | Admin dashboard + runtime config | src/server/modules/site-config/enums/site-config-key.enum.ts:7-9 only defines `GOOGLE_ADS_ID` for Google-related site-config; src/components/dashboard/site-config/config-editor.tsx:571-577 exposes only 'Google ADS Id' in the integrations tab; actual page tagging uses env-backed config in src/app/layout.tsx:31 and src/config/env.ts:240-244, while server-side GA reporting uses env-backed config in src/server/clients/google-analytics.service.ts:17-18. | Operators are shown a Google integration control panel that does not actually govern the live analytics implementation. That is a fake control surface and a reliable way to misconfigure production. | Either wire the admin UI to the real integration state or remove it. Keep Ads, GA tag ID, GA property ID, and service-account auth as explicit, separately documented settings.
A025 | Release engineering / Config | Hardcoded domains and localhost defaults still leak into auth, build config, and seeded content | 7 | Runtime config + seeded CMS content | src/server/auth/index.ts:489-492 falls back to `magasinetkbh.vercel.app` for cross-subdomain cookies; Dockerfile:46-60 bakes localhost and dummy host defaults into build-time auth/app/mobilepay env; src/server/database/seeders/page.seeder.ts:755-763 seeds `http://localhost:3000/faq`; src/app/(main)/payments/personal/page.tsx:28-52 and src/app/(main)/payments/sponsorship/page.tsx:20-44 hardcode live-domain share URLs and legacy asset URLs. | Wrong host defaults do not stay theoretical. They bleed into cookie scoping, generated links, seeded pages, and public marketing surfaces, which makes deployment behavior environment-dependent and error-prone. | Move every host/domain value behind validated configuration, remove hardcoded domains from seed data and page constants, and fail builds when required public URLs are missing instead of falling back to localhost or contractor domains.
A026 | Release engineering / Payments | Organization billing and seat-management logic still keys off dead business slugs and diverges from live profile state | 8 | Organization billing and seat-management APIs | src/server/auth/index.ts:226-250 remaps Better Auth subscription `plan` data around current price IDs; src/app/api/organization/dashboard/route.ts:13 and 150-157 filters `subscription.plan` against `['business-monthly', 'business-annual']`; src/app/api/organization/invitations/route.ts:14 and 73-80 repeats the same filter; src/app/api/organization/invitations/accept/route.ts:12 and 69-76 does it again during invitation acceptance. Live 2026-04-19: business-master@example.com sees an active organization subscription in `/api/organization/dashboard`, but `/profile` still says "Du kan tegne erhvervsabonnement på abonnements-siden." and "Ingen fakturaer fundet", showing that the business state does not resolve coherently across runtime surfaces. | A valid business subscription can be invisible to the organization dashboard, invitation flow, and seat enforcement because those routes still look for legacy slug strings instead of the live plan identity model. | Drive organization entitlement checks from normalized plan type or related price/plan records, not hardcoded legacy slug arrays.
A027 | Security / Release engineering | Dependency baseline is materially outdated and already carries critical/high vulnerabilities | 9 | Repo-wide runtime and build chain | Local `pnpm outdated --prod --format json` on 2026-04-17 reported 72 outdated top-level production dependencies. Examples include `next` 16.1.5 -> 16.2.4 ([package.json:136]), `drizzle-orm` 0.38.4 -> 0.45.2 ([package.json:121], [pnpm-lock.yaml:15867]), `@aws-sdk/client-s3` 3.907.0 -> 3.1031.0 ([package.json:49]), `@sentry/nextjs` 10.19.0 -> 10.49.0 ([package.json:90], [pnpm-lock.yaml:136]), `next-intl` 4.8.3 -> 4.9.1 ([package.json:137], [pnpm-lock.yaml:18046]), and `react` / `react-dom` 19.1.0 -> 19.2.5 ([package.json:148-151], [pnpm-lock.yaml:18725], [pnpm-lock.yaml:18632]). Local `pnpm audit --prod --json` on 2026-04-17 reported 78 production vulnerabilities: 3 critical, 39 high, 27 moderate, 9 low. Concrete runtime examples include direct `happy-dom` 18.0.1 ([package.json:127], [pnpm-lock.yaml:16774]) with a critical RCE advisory, direct `drizzle-orm` 0.38.4 with a high SQL-injection advisory, direct `next` 16.1.5 with a high denial-of-service advisory, critical `protobufjs` 7.5.4 via `@google-analytics/data` ([package.json:56], [pnpm-lock.yaml:18572]), and critical/high `fast-xml-parser` 5.2.5 via `@aws-sdk/client-s3` ([package.json:49], [pnpm-lock.yaml:16466]). | This is not a cosmetic 'updates available' complaint. The production dependency graph is both stale and already vulnerable in runtime-relevant packages. A production-ready release candidate should at minimum be on patched versions for known security advisories and should not lag this broadly across core framework, ORM, mail, analytics, and storage dependencies. | Upgrade direct production dependencies to current patched releases, eliminate critical/high advisories in runtime paths, refresh vulnerable transitive dependencies, and add a dependency-review cadence plus CI audit gating so the stack cannot drift back into this state.
A028 | Payments / Webhooks | Stripe webhook implementation is incomplete and misses business-critical invoice and payment lifecycle handling | 9 | Stripe webhook path and billing back office flows | Better Auth's Stripe docs state the plugin automatically handles only common subscription events (`checkout.session.completed`, `customer.subscription.created`, `customer.subscription.updated`, `customer.subscription.deleted`) and exposes `onEvent` for the rest: https://better-auth.com/docs/plugins/stripe. In this repo, src/server/auth/index.ts:383-452 wires `onSubscriptionComplete`, `onSubscriptionUpdate`, `onSubscriptionCancel`, and `onEvent`, but those handlers only create/cancel subscription metadata, log updates, and forward all other events to StripeWebhookService. src/server/modules/payment/services/stripe-webhook.service.ts:14-28 then handles only `product.created`, `product.updated`, `price.created`, and `price.updated`. src/server/modules/payment/services/invoice.service.ts:16-47 is read-only and just lists paid invoices directly from Stripe. By contrast, the legacy app had explicit business webhook handlers in __legacy/sites/all/modules/custom/mkbh_general/src/Stripe/Webhooks/Handlers/InvoicePaymentSucceeded.php:21-193 and InvoicePaymentFailed.php:16-65 that processed invoice success/failure, generated and stored business invoice PDFs, and triggered customer notifications. Live 2026-04-19: `/api/organization/dashboard` for the seeded business owner returned an active business subscription with `stripeSubscriptionId=null`, `stripeCustomerId=null`, and metadata.source=`codex-seed`, so the deployed state is not even pretending to be a synchronized Stripe record. | The billing surface looks integrated because Stripe checkout and Better Auth hooks exist, but the application does not own the revenue-critical lifecycle that the legacy system depended on. There is no evidence of explicit handling for invoice payment success/failure, charge lifecycle, customer lifecycle, business invoice persistence/PDF generation, or billing failure notifications. That is an incomplete Stripe setup, not a production-ready migration. | Implement explicit Stripe webhook handling for invoice, payment, charge, and customer lifecycle events; drive business-plan behavior from synchronized metadata rather than plan-name strings; persist invoice/business outcomes locally; and add replayable webhook tests covering the real event set before acceptance.
A029 | Payments / Billing | Stripe price handling has no authoritative source of truth and is split across DB sync, env-mapped IDs, and hardcoded business tariffs | 9 | Deployment bootstrap, public pricing pages, upgrade flow, and business checkout | src/server/auth/index.ts:239-250 tells Better Auth to load subscription plans from the local `plan_price` table, but there is no startup synchronization path: the only full catalog sync is the manual CLI command in src/server/commands/payment/stripe-fetch-plans.command.ts:1-23, while src/instrumentation.ts:20-49 does only env validation and Sentry startup. The DB seed path does not bootstrap Stripe pricing either: src/server/database/seeders/payment-plan.seeder.ts:207-224 and payment-price.seeder.ts:99-118 only update content on plans/prices that already exist and silently skip missing records. Personal upgrade billing then bypasses the local catalog and uses env-pinned Stripe price IDs in src/app/api/subscriptions/upgrade/route.ts:49-58 via config entries from src/config/env.ts:66-71 and 202-208. Business checkout goes the other direction and bypasses stored Stripe prices entirely by recalculating seat pricing from hardcoded tiers in src/server/auth/index.ts:268-366. The organization billing UI still contains a hardcoded business tariff table with an explicit TODO at src/app/(main)/profile/organization/_components/organization-content.tsx:19-91. Repo docs are also inconsistent, still instructing operators to replace hardcoded Stripe price IDs in `auth.ts` and separately noting that business pricing is handled by inline `price_data` in docs/stripe.md:133-142, 230-260, 669, 737. Live 2026-04-19: `/payments/business` exposed empty plan metadata in the serialized catalog, while `/payments/personal` still linked to `https://www.magasinetkbh.dk/profile` and hardcoded `2808` members plus `MobilePay 711911`. | This is split-brain billing. Depending on which path a user hits, price selection comes from the local DB, env-configured Stripe IDs, or hardcoded arithmetic in code. A fresh deployment can come up without synchronized Stripe plans/prices unless someone remembers to run a separate fetch command or receives the right webhooks, and the business checkout path can drift independently from whatever is shown in the stored catalog or dashboard. That is not production-ready pricing control. | Choose one authoritative pricing model and enforce it everywhere. Either sync Stripe products/prices into the app automatically during deployment/startup with hard failure on drift, or manage prices locally and generate Stripe catalog from that source. Remove env-based personal plan mapping, remove hardcoded business tariff tables and calculators that bypass stored prices, and add an explicit catalog-sync verification step to release/bootstrap.
A030 | Auth / Schema | Better Auth schema was hand-written instead of kept aligned with generated schema, and core auth/organization/subscription tables have already drifted | 8 | Core auth, organization, and billing data model | Better Auth's official CLI docs state that `generate` creates the schema required by Better Auth for Drizzle: https://better-auth.com/docs/concepts/cli. The repo contains a generated Better Auth schema snapshot at auth-schema.ts, but the live Drizzle schema is handwritten elsewhere and materially different. Concrete drift includes: generated SessionTable has `activeOrganizationId` at auth-schema.ts:31-50, but manual SessionTable in src/server/modules/auth/tables/session.table.ts:11-26 does not; generated OrganizationTable requires `slug`, stores `metadata` as text, and has no `updatedAt` at auth-schema.ts:92-108, while src/server/modules/organization/tables/organization.table.ts:14-29 makes `slug` nullable, uses JSON metadata, and adds `updatedAt`; generated SubscriptionTable at auth-schema.ts:151-169 includes `cancelAt`, `endedAt`, `billingInterval`, `stripeScheduleId`, and default `status="incomplete"`, while src/server/modules/payment/tables/subscription.table.ts:21-48 omits those fields and adds its own `provider`, `period`, `plan`, `metadata`, `limits`, and `userId`; generated UserTable uses text IDs and text `avatarId` at auth-schema.ts:12-29, while src/server/modules/user/tables/user.table.ts:18-37 uses UUID IDs, UUID avatar FK, and extra `firstName`/`lastName`; generated InvitationTable makes `inviterId` required with cascade and `role` optional at auth-schema.ts:129-149, while src/server/modules/organization/tables/invitation.table.ts:14-30 makes `inviterId` nullable with `set null`, requires `role`, and adds `updatedAt`. The repo also keeps a manual two-factor table at src/server/modules/auth/tables/two-factor.table.ts:10-21 even though the current auth config in src/server/auth/index.ts:135-470 does not enable the Better Auth 2FA plugin and the generated schema snapshot contains no two-factor table. | This is not an abstract style preference. The authentication, organization, and Stripe subscription plugins are being run against a handwritten schema that already diverges from the schema Better Auth generates for the current config. That creates latent breakage around active organization switching, invitation semantics, subscription lifecycle fields, future Better Auth upgrades, and any migration or support work that assumes generated-schema parity. | Regenerate the Better Auth schema from the current auth config, reconcile the handwritten Drizzle tables to match it or explicitly map every intentional deviation, remove dead auth tables that are not backed by enabled plugins, and add a CI drift check so generated auth schema changes cannot silently diverge from the live database model.
A031 | Security / Authorization | Back-office content, billing, config, media, and duplicate user-admin pages are exposed to every authenticated role | 9 | Any logged-in user, editor, journalist, or business account | Live 2026-04-19 route probes returned HTTP 200 for `/dashboard`, `/dashboard/posts/new`, `/dashboard/content/polls/new`, `/dashboard/posts/tags`, `/dashboard/payment`, `/dashboard/config`, `/dashboard/media`, `/dashboard/media/create-many`, `/dashboard/paywall-bypass/tokens`, and the duplicate `/dashboard/admin/users` page for user@example.com, editor@example.com, journalist@example.com, business-master@example.com, business-employee@example.com, and admin@example.com. Only `/dashboard/auth/users` stayed admin-only; `/dashboard/admin/users/create` returned 404 for every tested role. Code path: src/app/dashboard/layout.tsx:22 and src/lib/trpc/trpc.ts:56 gate only on session presence. | This is not a cosmetic menu leak. Ordinary authenticated users can enter authoring, tag, media, billing, configuration, paywall-bypass, and duplicate user-admin surfaces, which materially widens the attack surface and acceptance risk even before you test write operations. | Apply explicit role gates at the dashboard layout and route level, default-deny admin/config/payment/media surfaces, and add role-matrix integration tests so these pages cannot regress back to session-only access.
A032 | Payments / Acceptance truthfulness | Live business subscriptions are demo-seeded state disconnected from Stripe and misrepresented in profile self-service | 10 | Seeded business subscriber accounts | Live 2026-04-19: `/api/organization/dashboard` for business-master@example.com returned organization `Railway Test Business` with active `business-monthly` status, 5 seats, 2 used seats, metadata.source=`codex-seed`, and both `stripeSubscriptionId` and `stripeCustomerId` null. The same account's `/profile` page still tells the owner `Du kan tegne erhvervsabonnement på abonnements-siden.` and shows `Ingen fakturaer fundet`. | The deployed acceptance environment can demonstrate “working” business subscriptions without any real Stripe-backed billing record or coherent self-service state. That is exactly the kind of fake-complete commerce surface that should block sign-off. | Remove demo-seeded billing state from acceptance environments, sync real Stripe customer/subscription identifiers into the authoritative subscription record, and render business billing/profile screens from that single source of truth.
A033 | Payments / Deceptive UX | Public business success page confirms subscription without validating any checkout session | 9 | Public route | Live GET `https://mkbh-dev.up.railway.app/payments/success?type=business` returned HTTP 200 anonymously on 2026-04-19 and displayed `VELKOMMEN! Du er nu abonnent på Magasinet KBH...` plus `Begynd at læse`, without any visible order/session identifier or gate proving a completed checkout. | This can falsely signal successful billing, mask broken checkout/session wiring, and mislead both users and acceptance reviewers into believing the business purchase flow completed when nothing was validated. | Require a verified Stripe checkout session or signed completion token before rendering success copy; otherwise redirect to an error or restart page.
A034 | Access control / Paywall | Live paywall behavior is inconsistent: KBH+ stays locked for business subscribers while Visioner unlocks body text for any logged-in user | 9 | Public article routes and logged-in user/business sessions | Live 2026-04-19: `/inhold/kbh-plus-saerlig-daekning-8` showed the paywall CTA `Få adgang som medlem eller abonnent` and `Bliv medlem` for anonymous, regular-user, and business-master sessions alike, while still exposing comment markers on the locked page. On `/visioner/vision-for-kobenhavns-fremtid-7`, the ordinary `user@example.com` session received an extra article-body paragraph that anonymous visitors did not get, even though that account is not a paying subscriber. Relevant code paths were already confirmed in src/app/(main)/inhold/[slug]/page.tsx and the Visioner post-grid/page components. | The entitlement model is broken in both directions: paying business users may not receive access where they should, and ordinary registered users can receive subscriber-only content on other families. That is acceptance-critical because the publication's monetization rules are inconsistent and non-deterministic. | Centralize entitlement checks across all content families, include business-organization entitlements in the same policy, and add anon/member/personal-subscriber/business-subscriber regression tests on every gated template.
A035 | Security / Quality | Auth session payload leaks dev-only `dd: "test"` field for every authenticated user | 4 | Every authenticated session payload | Live 2026-04-19: `/api/auth/get-session` for admin, editor, journalist, user, business-master, and business-employee accounts all returned a `user.dd = "test"` field alongside the normal session payload. | This is low severity compared with the billing and authorization failures, but it is direct runtime evidence that test/debug data is leaking through the production auth serializer and that the deployed response contract is not cleanly controlled. | Remove debug fields from the serialized auth/session payload and add an API contract test that fails if unexpected user properties leak into the client session response.
A036 | Release engineering / Config | Configuration has no single source of truth across env files, runtime validation, DB-backed settings, and startup defaults | 8 | Repo-wide / deployment path | src/instrumentation.ts:22-31 imports env validation at Node startup; src/config/env.ts validates 54 runtime keys and hard-requires Stripe/MobilePay values, while `.env.example` documents 60 keys with 20 compose/bootstrap-only entries and omits 14 runtime keys, including all Stripe price IDs plus Sentry/DEBUG/LOG_LEVEL. Mailchimp is split between env-backed list selection in src/server/modules/newsletter/services/newsletter.service.ts:17-18 and DB-backed API-key lookup in src/lib/mailchimp/client.ts:6-12 via publicly readable site-config values at src/server/modules/site-config/router/index.ts:7-11 and services/site-config.service.ts:19-29. GA is split across env tag/property settings in src/app/layout.tsx:28 and src/config/env.ts:91-93 plus file-path ADC assumptions in `.env.example`:70 and src/server/clients/google-analytics.service.ts:15-17. | Operators cannot trust a single deploy contract. Bringing the app up on a real server requires reverse-engineering which settings belong in env, which are hidden in the database, and which still depend on localhost or credential-file assumptions. That is a production-readiness failure, not a documentation nit. | Define one authoritative configuration contract: keep secrets and deploy-time settings in env only, remove secret-bearing public site-config reads, make the example env file match the runtime schema, delete dev/bootstrap-only keys from production docs, and decouple startup from unrelated payment integrations.

## Mock Findings
Mock Findings
Surfaces where the implementation presents itself as functional while relying on reduced or fake behavior.
id | surface | type | evidence | user_visible_effect | severity
M001 | Archive page | hardcoded data | src/app/(main)/arkiv/page.tsx:19-99 defines a fixed `items` array with five records and repeated image/pdf assets while the page copy claims all 57 issues are available. | Users see something that looks like an archive, but it is a fabricated five-row sample instead of the real legacy archive. | 10
M002 | Newsletter page | dead submit handler | src/app/(main)/nyhedsbrev/_components/newsletter-form.tsx:35-39 leaves the submit action as a comment placeholder. | The primary newsletter signup page looks complete, accepts input, and then does nothing. | 10
M003 | Subscription upgrade | stubbed backend | src/server/modules/payment/services/subscription.service.ts:170-175 returns `{}` from `upgrade()` while src/components/payment/blocks/subscription-card.tsx:144-151 still calls it. Live 2026-04-19: POST `/api/trpc/payment.subscription.upgrade` returned empty JSON for both the personal subscription `e7e15246-bb32-44ef-8551-cf136679505b` and the seeded business subscription `24ea47e5-ab49-4a8f-8358-a126131485d0`. | Users are offered an upgrade flow that is not implemented. | 10
M004 | Project alerts | misrepresented behavior | src/components/shared/post-newsletter-form.tsx:61-69 sends only `{ email }` to the generic newsletter mutation, despite CTA copy promising project-specific alerts. | The UI claims project update alerts, but the implementation is just a generic newsletter signup. | 9
M005 | Public Stripe test page | demo/test surface | src/app/test-stripe/page.tsx:8-195 ships a public demo control panel for test subscription and organization actions. Live GET `https://mkbh-dev.up.railway.app/test-stripe` returned HTTP 200 on 2026-04-19. | A non-customer demo flow is presented on the public app surface. | 8
M006 | Personal payments page | hardcoded marketing data | src/app/(main)/payments/personal/page.tsx:136-175 hardcodes `2808` members and `MobilePay 711911`; lines 28-52 use legacy asset URLs. Live 2026-04-19: `/payments/personal` rendered all three of those values directly in the public page HTML, including a hardcoded link to `https://www.magasinetkbh.dk/profile`. | The page mixes real dynamic plan data with fake/static proof points that can mislead acceptance review and end users. | 7
M007 | Sponsorship page | manual fallback posing as productized flow | src/app/(main)/payments/sponsorship/page.tsx:92-97 converts through `mailto:` and lines 20-44 and 111-117 pull legacy-hosted assets. Live 2026-04-19: `/payments/sponsorship` exposed a `mailto:sponsor@magasinetkbh.dk?...` CTA in public HTML rather than a real checkout or self-service flow. | The surface looks migrated, but conversion is still manual and piggybacks on legacy assets. | 6
M008 | Guest links | reduced implementation sold as full feature | src/components/dashboard/post/post-guest-link-dialog.tsx:17-66 only supports an optional expiration date; it does not implement the requested one-time mode and builds the link with raw `token` querystring. | Editors are given a 'guest link' tool that looks finished, but it omits key promised behavior. | 6
M009 | Organization pricing component | dead hardcoded fallback | src/app/(main)/profile/organization/_components/organization-content.tsx:19-110 contains a hardcoded business plan table and `currentPlan` fixed to `undefined`, but the active route uses a different component. | Not currently user-visible on the active route, but it is still unfinished fallback code that imitates real pricing logic. | 3
M010 | Google Analytics sync | hardcoded fake data | src/server/clients/google-analytics.service.ts:102 injects `/kort/test` with 1000 views, and src/server/commands/update-ga-page-views.command.ts:14-23 persists that fabricated row like real analytics data. | Analytics can appear populated and healthy even when part of the dataset is synthetic contractor filler. | 9
M011 | Business payment success page | fake success flow | Live GET https://mkbh-dev.up.railway.app/payments/success?type=business returned HTTP 200 anonymously on 2026-04-19 and rendered `VELKOMMEN! Du er nu abonnent på Magasinet KBH...` plus `Begynd at læse` without any verified checkout state. | Anyone can hit a URL and see copy that claims the subscription succeeded, which can hide broken billing wiring during acceptance and confuse end users after failed checkout attempts. | 9
M012 | Business subscription profile | seeded demo state presented as live billing | Live 2026-04-19: `/api/organization/dashboard` returned active business-monthly state with metadata.source=`codex-seed` and null Stripe IDs, while `/profile` for the same owner still invited them to buy a business subscription and showed `Ingen fakturaer fundet`. | The environment looks as if business billing and seat management exist, but the underlying state is contradictory demo data rather than a coherent production subscription record. | 9
M013 | Business pricing catalog | empty synced catalog metadata | Live `/payments/business` serialized price rows with `name:""`, `description:""`, and `content:{}` while the page still rendered tier prices and quantity selectors. | Users are shown a checkout-ready pricing surface whose core plan metadata is blank, making the page look integrated while the underlying catalog is only half-populated. | 8

## Appendix
Appendix
Optional, withdrawn, and out-of-scope rows separated from pass/fail scoring.
id | capability | scope_modifier | verdict | notes
F019 | Pre-launch data migration | out_of_scope | Skipped | Not scored in acceptance verdict for this report.
F045 | Inline CityChange single-suggestion widget with ID field and address override | withdrawn | Partial | Withdrawn from pass/fail scoring because the spec later deletes this as net-new scope.
F055 | Drag-and-drop reordering of inline-image placeholders | optional | Skipped | Kept in appendix scoring only; does not drive refund on its own.
F056 | Edit inline-image captions directly from the thumbnail UI | optional | Full | Optional item; implemented.
F060 | Use additional 'Publish' title font pre-launch | withdrawn | Skipped | Withdrawn requirement; excluded from pass/fail scoring.